## Sheet1
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Patient Recruited? | Date of First Patient Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Patient Recruited | Duration between Date Site Selected and First Patient Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
16/HRA/5525 | 210175 | Investigation of wellbeing interventions in NHS staff | Yes | 2018-02-27 | 15 | 12 | 27 | 2018-01-30 | 2018-01-31 | 2017-01-23 | 2018-02-01 | 2018-02-15 | 2018-02-21 | Please Select...
18/SC/0104 | 240005 | EFFIP (E-support for Families and Friends of Individuals affected by Psychosis): A randomised controlled trial of a co-produced online intervention for carers | Yes | 2018-04-17 | 0 | 27 | 27 | 2018-01-10 | 2018-03-01 | 2018-02-02 | 2018-03-07 | 2018-03-21 | 2018-03-26 | Please Select...
17/LO/0030 | 200764 | CST in people with Intellectual disability and dementia | Yes | 2018-09-18 | 29 | 34 | 63 | 2018-04-10 | 2018-07-17 | 2017-05-11 | 2018-07-17 | 2018-08-15 | 2018-08-16 | Sponsor