## Sheet1
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Date Site Ready To Start | Reasons for delay correspond to:
17/LO/0987 | 215947 | A feasibility study and pilot trial of a modified video-feedback intervention for children and foster carers to improve mental health outcomes of children with reactive attachment problems (VIPP-FC) | 2019-04-05 | 2017-12-07 | 2018-12-17 | 2017-08-18 | 2019-01-14 | 2019-01-14 | 2019-01-15 | Neither
18/YH/0499 | 258585 | Smoking Cessation Intervention for Severe Mental Ill Health Trial (SCIMITAR): a definitive randomised evaluation of a bespoke smoking cessation service. Extended follow up. | 2019-03-14 | 2018-12-10 | 2019-02-11 | 2019-01-09 | 2019-01-25 | 2019-03-08 | 2019-03-11 | n/a
19/LO/0088 | 257667 | A randomised controlled trial of a structured intervention for expanding social networks in psychosis | 2019-04-15 | 2018-10-16 | 2019-04-09 | 2019-01-24 | 2019-04-15 | 2019-04-15 | 2019-04-15 | n/a
18/WA/0209 | 238724 | Problem Adaptation Therapy For Depression in Dementia | n/a | 2019-05-02 | 2019-07-29 | 2018-06-25 | 2019-07-29 | 2019-09-09 | 2019-09-12 | n/a
Note on E1: Format dd/mm/yyyy.
Note on F1: Format dd/mm/yyyy.
Note on G1: Format dd/mm/yyyy.
Note on H1: Format dd/mm/yyyy.
Note on I1: Format dd/mm/yyyy.
Note on J1: Format dd/mm/yyyy.